## Tasks
Key | Folder | Parent task | Title | Workflow | Status | Custom status | Priority | Assigned To | Start Date | Duration | Duration (Hours) | Time Spent (Hours) | End Date | Depends On | Start Date Constraint | Description
1 | / |  | Bill the Client | Default Workflow | Active | Active | Normal |  | 2016-01-12 | 1 day | 0.33333 |  | 2016-01-12
2 | / |  | Pay the Application Fee | Default Workflow | Active | Active | Normal |  | 2016-01-12 | 1 day | 0.33333 |  | 2016-01-12
3 | / |  | Obtain Client Instructions | Default Workflow | Active | Active | Normal |  | 2016-01-04 | 1 day | 0.33333 |  | 2016-01-04
4 | / |  | Perform AML Check | Default Workflow | Active | Active | Normal |  | 2016-01-04 | 1 day | 0.33333 |  | 2016-01-04
5 | / |  | Perform Conflict Check | Default Workflow | Active | Active | Normal |  | 2016-01-04 | 1 day | 0.33333 |  | 2016-01-04
6 | / |  | Arrange Donor and Donees to meet and to execute LPA | Default Workflow | Active | Active | Normal |  | 2016-01-05 | 1 day | 0.33333 |  | 2016-01-05
7 | / |  | Draft LPA Form | Default Workflow | Active | Active | Normal |  | 2016-01-05 | 1 day | 0.33333 |  | 2016-01-05
8 | / |  | Review LPA by Partner Form | Default Workflow | Active | Active | Normal |  | 2016-01-05 | 1 day | 0.33333 |  | 2016-01-05
9 | / |  | Revise LPA Form | Default Workflow | Active | Active | Normal |  | 2016-01-06 | 1 day | 0.33333 |  | 2016-01-06
10 | / |  | Send to Client for Review | Default Workflow | Active | Active | Normal |  | 2016-01-07 | 1 day | 0.33333 |  | 2016-01-07
11 | / |  | Meet with Donor and Donees for Execution | Default Workflow | Active | Active | Normal | [5 empty] | 2016-01-11
12 | / |  | Complete LPA Application Form | Default Workflow | Active | Active | Normal |  | 2016-01-08 | 1 day | 0.33333 |  | 2016-01-08
13 | / |  | Obtain NRIC of Donees | Default Workflow | Active | Active | Normal |  | 2016-01-11 | 1 day | 0.33333 |  | 2016-01-11
14 | / |  | Obtain NRIC of Donor | Default Workflow | Active | Active | Normal |  | 2016-01-11 | 1 day | 0.33333 |  | 2016-01-11
15 | / |  | Post the LPA Application to the Office of Public Guardian | Default Workflow | Active | Active | Normal |  | 2016-01-13 | 1 day | 0.33333 |  | 2016-01-13